## Project plan
Applicant: |  | Project name:
Steingerður Jósepsdóttir
Project plan and timeline
Here you define tasks as appropriate for your project, estimate time frames and assign responsibilities. Total cost figures for each task are automatically retrieved from the cost estimate.
Task | Start | End | Responsibility | Cost
Preparation | 2023-10-18 | 2024-03-30 | Steingerður Jósepsdóttir | 543000
Execution | 2024-01-08 | 2024-06-30 | Steingerður Jósepsdóttir | 1383000
Follow-up | 2024-04-01 | 2024-09-30 | Flóvent Sveinbjörnsson | 75200
Estimated start and end of project | 2023-10-18 | 2024-09-30 | Estimated total project cost | 2001200
Formulas:
Start = SUBTOTAL(105,Project_plan[Start])
End = SUBTOTAL(104,Project_plan[End])
Tips and advice
A well thought out project plan is the basis of successful project management. Do you think your project plan is credible? Is the plan likely to make your idea a reality?
It depends on the nature and scope of the project how, and whether, it is desirable to divide it into tasks or work components.
Some projects are carried out in phases that could be specified as work components or Tasks, e.g.
Preparation
Execution
Follow-up
Some projects include more than one product that could be defined as tasks or work components, e.g.
Market research
Business plan
Website
Note that a task/work component is not a single activity. An activity can be a specific cost connected with a task.
Example: Say the project is an art event and the project is devided into the tasks Preperation, Execution and Follow-up, one of the activities might be reimbursing the artists, which would be a cost, part of the task Execution. The monetary payment would be one cost, and the activity (time spent doing it) would be another cost.
Please note that costs incurred before the end of the application deadline are not eligible for funding.

## Cost estimate
Cost estimate
Here you itemise all eligible costs that the project calls for and connect each cost item to the task it belongs to. Tasks you defined in the project plan appear in the drop-down list for the task in the table below. If you need to add a task, go back to the project plan tab and create a new task there.
Cost item | Task | Units | Unit price | Total
Preparatory meetings of partners | Preparation | 18 | 4700 | 84600
Preparation of drama workshop | Preparation | 36 | 4700 | 169200
Work on costumes and props | Preparation | 36 | 4700 | 169200
Materials for costumes and props | Preparation | 1 | 120000 | 120000
Author's remuneration | Execution | 1 | 380000 | 380000
Acting workshops | Execution | 10 | 50000 | 500000
Driving | Execution | 750 | 204 | 153000
Music performance | Execution | 10 | 35000 | 350000
Picture book and student newspaper article | Follow-up | 16 | 4700 | 75200
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total project cost |  |  |  | 2001200
Tips and advice
The cost estimate (or budget) is a breakdown of eligible project costs, linked to project tasks. Each task can contain one or more cost items which can either be direct paid expences or worktime spent on the project.
A detailed and credible budget shows good preparation. Cost figures must be realistic, neither exaggerated nor underestimated, and try to anticipate all necessary cost items.
Do not enter large numbers without explanation, specify quantity and unit price.
A cost estimate should show the total of eligible costs of the project applied for here.
Familiarize yourself with the allocation rules for which costs are eligible for funding and the maximum hourly rate that can be calculated for your own work contribution.

## Funding plan
Funding plan
The Development Fund generally funds no more than 50% of the eligible total cost of projects. The applicant must therefore finance the rest. This can fore example be done with own work contribution, own financial contribution, other grants, income from the project etc. |  |  | Balancing - (totals from current plans)
|  |  | Total project cost | 2001200
|  |  | Total funding | 2001200
|  |  | Funding balance | 0
Maximum grant based on current cost estimate is | 1000600
Project is fully funded
Funding | Amount | % of cost
Northeast Iceland Development fund - amount applied for | 1000000 | 49.97%
Grant from KEA | 100000 | 4.997%
Grant from Barnamenningarsjóður | 300000 | 14.99%
Own work contribution | 498200 | 24.9%
Own financial contribution (driving cost) | 103000 | 5.147%
Total | 2001200 | 100%
Tips and advice
Funding is simply about who pays the estimated cost of the project.
Note that funding should be exactly 100%
If funding is below 100%, it suggest that the project can not be completed. If funding is over 100%, it indicates that the grant amount applied for is not needed.
Try increasing or decreasing a funding item and see what happens in Balancing above.

## Cost recording
Cost recording for reports |  |  |  |  | Funding (confirmed) | Amount | % of cost
This tab is intended to assist you with preparing progress or final reports. Here you can keep track of project costs as they occur. The Tasks you defined in the project plan appear in a drop-down list for the task in the table below. |  |  |  |  | Northeast Iceland Development fund - current grant
[5 empty] | Total funding | 0 | 0%
Cost item | Task | Units | Unit price | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total project cost |  |  |  | 0

## Time log
Time recording for own work contribution
Here you can keep track of work put into the project without compensaton. According to the allocation rules, the maximum hourly fee can not excede ISK. 4,700. Note that work paid for according to invoice or payslip is transferred as an paid out cost and is not recorded as own work contribution.
Date | Name of person | Task | Hours | Rate | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total |  |  | 0 |  | 0
Helpful tool
We encourage you to log your own work contribution on a regluar basis. Experience has shown that when trying to estimate your time after the fact, when a progress or final report is due, most people tend to underestimate the time spent on the project.